## Summary
Item Code | Project Name | Order/shipment | Short spec | Supplier | FOB | Qty | PI date | PR | IMEI TAC | BTRC Imp. NOC | Material desc. | Shipment Date | Shipment status | Factory In Date | BTRC MKT NOC | IMEI upload | Colors | Remarks
874048 | EVO | 6th | 2'', MTK6261M, 3000 mAh, F7 torch, camera | Kingcomm | 4.53 | 20000 | 2025-06-28 | 55510048457 | 35743716 | 14.32.0000.000.501.47.0005.20.1116 | Charger : CKD without housing, Battery: SKD |  | Shipped |  |  |  |  | Denny's Jig will be shipped with this shipment
751046 | Star | 2nd | 2.4'', MTK6261M, 1900 mAh, F3 torch, camera, Type C | Kingcomm | 5.03 | 15000 | 2025-06-28 | 55510048454 | 35099786 | 14.32.0000.000.501.47.0005.20.655 | Charger : CKD without housing, Battery: CBU |  | Shipped
874050 | Hulk | 3rd | 2.4'', MTK6261D, 3000 mAh, strip torch, camera | Kingcomm | 5.41 | 10000 | 2025-06-29 | 55510050040 | 35820468 | 14.32.0000.000.501.47.0005.20.1116 | Charger : CKD without housing, Battery: SKD |  | Shipped
751312 | i-Pro | 1st | 2'', MTK6261M, 1000 mAh, F5 torch, no camera, Type C | Kingcomm | 3.84 | 20000 | 2025-06-29 | 55510051313 | 35176552 | 14.32.0000.000.501.47.0005.20.1346 | Charger : CKD without housing, Battery: SKD | [5 empty] | • Black Olive- 10k • Black Red- 4k • Black Blue- 6k
751047 | Neo | 1st | 2'', MTK6261M, 2500 mAh, F7 torch, camera, Type C | IMG | 4.2 | 15000 | 2025-06-27 | 55510051312 | 35901568 | Need to apply | Charger : CKD without housing, Battery: SKD | [6 empty] | Inventory wrongly created another PR for NEO 55510051314
751239 | Glory i30 | 1st | MTK G50; LCD: 6.745", HD+, 90Hz; RAM+Memory：4GB (SW boosted 12GB) +128GB(EMCP DDR4X); Camera : 5MP ( 8MP by SW) & 13MP( 50MP by SW) + 2.0MP+0.3MP; 6000mAh; Android 15 | Coosea | 48.7 | 6000 | 2025-05-27 | 55510047928 | 35560026 | 14.32.0000.000.501.47.0005.20.1245 | Charger : No | 2025-09-10 | [5 empty] | 3K Black 3K Grey
874789 | X10 Pro | 3rd | T606, LCD: 6.56", HD+; RAM+Memory：4GB (SW boosted 8GB) +128GB; Camera : 5MP ( 8MP by SW) & 13MP( 50MP by SW) + CIF+CIF; 5000mAh; Android 14 | I-Swim | 53.5 | 4000 | 2025-03-13 | applied - need to follow up | 35453426 | 14.32.0000.000.501.47.0005.20.696 | Charger : No |  | Shipped
751044 | PowerX | 2nd | 2.4'', MTK6261M, 3000 mAh, F7 torch, camera, Type C | Kingcomm | 5.04 | 10000 | 2025-07-03 | 55510050041 | 35334484 | 14.32.0000.000.501.47.0005.20.477 | Charger : CKD without housing, Battery: CBU
874787 | ECO | 6th | 1.77'' MTK6261M, 1000 mAh , no camera | Kingcomm | 3.65 | 20000 | 2025-07-17 | 55510050042 | 35664453 | 14.32.0000.000.501.47.0005.20.1116 | Charger : CKD without housing, B type cable, Battery: CBU
751311 | Blast 3D | 1st | 2.4'' , MT6261M, 3000 battery, 2030 BOX SPEAKER , D8 spot torch, camera | IMG | 5.4 | 15000 | 2025-07-18 | 55510051315 | 35901568 | Need to apply | Charger : CKD without housing, Type C cable Battery: CBU
751310 | HyperX | 1st | Chipset: Helio G100 Memory: 8+128 Display: 6.78' FHD+, Hole-punch Display Front Camera:32MP(50MP by SW) Rear Camera:64MP+2MP+VGA (108MP by SW) Battery:6000mAh Side Fingerprint Unlock PMMA Back Cover TPU 33W TYPE-C | Coosea | 73.3 | 3000 | 2025-07-31 | 55510052181 | HYPERX20250927 |  | Charger : No
874050 | Hulk | 4th | 2.4'', MTK6261D, 3000 mAh, strip torch, camera | Kingcomm | 5.41 | 15000 | 2025-08-06 | 55510051589 | 35820468 | 14.32.0000.000.501.47.0005.20.1116 | Charger : CKD without housing, Battery: SKD
751046 | Star | 3rd | 2.4'', MTK6261M, 1900 mAh, F3 torch, camera, Type C | Kingcomm | 5.03 | 20000 | 2025-08-06 | 55510051590 | 35099786 | 14.32.0000.000.501.47.0005.20.1245 | Charger : CKD without housing, Battery: CBU
874048 | EVO | 7th | 2'', MTK6261M, 3000 mAh, F7 torch, camera | Kingcomm | 4.53 | 40000 | 2025-08-06 | 55510051588 | 35743716 | 14.32.0000.000.501.47.0005.20.1116 | Charger : CKD without housing, Battery: SKD | [6 empty] | Denny's Jig will be shipped with this shipment
751044 | PowerX | 3rd | 2.4'', MTK6261M, 3000 mAh, F7 torch, camera, Type C | Kingcomm | 5.04 | 10000 | 2025-08-06 | 55510051591 | 35334484 | 14.32.0000.000.501.47.0005.20.1245 | Charger : CKD without housing, Battery: CBU | [6 empty] | BTRC NOC expiary date 4th September, 2025
751342 | King | 1st | Display:1.77'' Chipest:6531E Camera with flash, No Torch, Memory:32M+32M Speaker:2030， Type C | T-World | 4.7 | 15000 | 2025-08-23 | 55510052902 | 35524369 | Need to apply | Project: SKD, Charger: No, Battery : CBU
751343 | Jet4g | 1st | 2.4 inch QVGA ( T127) Battery : 2000 mAh Wireless FM Camera - Front: 0.08MP, Rear: 0.08MP+flash | Kingcomm | 10.9 | 5000 | 2025-08-22 | 55510052903 | 35901568 | Need to apply | Project: SKD, Charger : CKD without housing Type C cable, Battery: SKD | [6 empty] | Previous PR was created for 3K qty 55510051316
| Style CKD | 1st | 2.4'' QVGA, SC6533G -Battery : 2500 mAh - speaker, Receiver& Vibrator 3 in 1 , no camera -Wireless -FM , F7 Torch | Kingcomm | 4.48 | 30000 | 2025-08-22 | applied |  |  | Handset: CKD Charger : CKD without housing, Type C cable, Battery: SKD | [6 empty] | According to PI - Kingcomm will provide FOC , the ratio : PCBA+LCD+CAM+BATTERY+ KEYPAD 0.5% ; other materials 1% , mylars 2%，labels 2% , battery SKD materials 2%
751312 | i-Pro | 2nd | 2'', MTK6261M, Battery : 1000 mAh, F5 torch, no camera, Type C | Kingcomm | 3.7 | 20000 | 2025-09-24 | 55510054528 | 35176552 | Need to apply | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD | [6 empty] | According to PI - Kingcomm will provide FOC , the ratio : PCBA+LCD+CAM+BATTERY+ KEYPAD 0.5% ; other materials 1% , mylars 2%，labels 2% , battery SKD materials 2%
874787 | ECO | 7th | 1.77'' MTK6261M, 1000 mAh , no camera | Kingcomm | 3.48 | 30000 | 2025-09-24 | applied | 35664453 | 14.32.0000.000.501.47.0005.20.1116 | Handset: SKD Charger : CKD without housing, B type cable, Battery: SKD | [6 empty] | According to PI - Kingcomm will provide FOC , the ratio : PCBA+LCD+CAM+BATTERY+ KEYPAD 0.5% ; other materials 1% , mylars 2%，labels 2% , battery SKD materials 2%
874199 | ECO25 | 3rd | 1.77'' QQVGA, MTK6261M, 1000 mAh, no camera, Wireless FM, F5 torch | Kingcomm | 3.56 | 15000 | 2025-09-24 | applied | 35247922 | 14.32.0000.000.501.47.0005.20.1346 | Handset: CKD Charger : CKD without housing, B type cable, Battery: SKD | [6 empty] | At first the project was 20K SKD, then it was converted to 15K CKD . Battery converted to SKD from CBU
751043 | E30 | 3rd | 2.4'' QQVGA, MTK6261M, 2000 mAh, no camera, Wireless FM, F5 torch | Kingcomm | 4.6 | 20000 | 2025-09-24 | applied | 35855831 | 14.32.0000.000.501.47.0005.20.1346 | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD | [6 empty] | Battery changed to SKD from CBU
| Glow | 1st | 2.8'' QVGA, MTK6261M, Battery : 2500 mAh, speaker, Receiver& Vibrator 3 in 1 , VGA camera, Wireless FM, F8 Torch | Kingcomm | 5.2 | 20000 | 2025-09-24 | applied |  |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD
874048 | EVO | 8th | 2'', MTK6261M, 3000 mAh, F7 torch, camera | Kingcomm | 4.3 | 40000 | 2025-09-24 | applied | 35743716 | 14.32.0000.000.501.47.0005.20.1346 | Handset: SKD Charger : CKD without housing, Type B Cable. Battery: SKD
874050 | Hulk | 5th | 2.4'', MTK6261D, 3000 mAh, strip torch, camera | Kingcomm | 5.25 | 20000 | 2025-09-24 | applied | 35820468 | 14.32.0000.000.501.47.0005.20.1116 | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD
751044 | PowerX | 4th | 2.4'', MTK6261M, 3000 mAh, F7 torch, camera, Type C | Kingcomm | 4.8 | 20000 | 2025-09-24 | applied | 35334484 | 14.32.0000.000.501.47.0005.20.1245 | Handset: SKD Charger : CKD without housing, Type C cable, Battery: CBU

## Mobile
| Jet 4g |  |  |  | King |  |  |  | HyperX |  |  |  | Glory i30 |  |  |  | i-Pro |  |  |  | Neo |  |  |  | Blast 3D
Milestone | Planned | Actual | Status | Note | Planned | Actual | Status | Note | Planned | Actual | Status | Note | Planned | Actual | Status | Note | Planned | Actual | Status | Note | Planned | Actual | Status | Note | Planned | Actual | Status | Note
PI Confirmation | 2025-08-23 | 2025-08-23 | Completed |  | 2025-08-23 | 2025-08-23 | Completed |  | 2025-08-07 | 2025-08-07 | Completed |  | 2025-05-25 | 2025-05-25 | Completed |  | 2025-06-28 | 2025-06-28 | Completed |  | 2025-06-26 | 2025-06-26 | Completed |  | 2025-07-17 | 2025-07-17 | Completed
ID confirmation |  |  | Completed |  | 2025-08-28 | 2025-09-01 | Completed |  | 2025-08-02 | 2025-08-02 | Completed |  | 2025-06-03 | 2025-08-03 | Completed |  | 2025-06-30 | 2025-07-02 | Completed |  | 2025-06-24 | 2025-06-24 | Completed |  | 2025-08-01 | 2025-08-01 | Completed
LC Transmit |  |  | Pass |  |  |  | Pass |  |  |  | Pass |  | 2025-07-25 | 2025-07-25 | Completed |  | 2025-07-15 | 2025-07-25 | Completed |  |  |  | Pass |  |  |  | Pass
PR | 2025-08-31 | 2025-08-31 |  | 55510052903 | 2025-08-31 | 2025-08-31 |  | 55510052902 | 2025-08-20 | 2025-08-20 |  | 55510052181 | 2025-06-05 | 2025-06-05 | Completed | 55510047928 | 2025-07-02 | 2025-07-02 | Completed | 55510051313 | 2025-07-08 | 2025-07-30 | Completed | 55510051312 | 2025-07-28 | 2025-07-30 | Completed | 55510051315
Color confirmation | [12 empty] | 2025-07-29 | 2024-06-21 | Completed |  | 2025-08-01 |  | Started |  | 2025-08-01 | 2025-08-01 | Completed |  | 2025-08-19 |  | Started
Sample(for HW and SW testing) | [8 empty] | 2025-10-10 |  |  |  | 2025-07-28 | 2025-07-26 | Completed |  | 2025-08-13 | 2025-09-10 | Completed | Waiting for sample. Supplier would send sample on 20th August | 2025-08-10 |  | Not Started | Waiting for the sample | 2025-09-28 |  |  | Waiting for the sample
BOM Material Confirmation | [12 empty] | 2025-07-12 | 2025-08-13 | Completed |  | 2025-08-24 | 2025-09-22 | Completed | Waiting for sample | 2025-08-15 |  | Not Started | Our supplier is preapring HS sample | 2025-10-13 |  |  | Our supplier is preapring HS sample
BTRC sample(With Logo) | [8 empty] | 2025-10-10 |  |  |  | 2025-08-22 | 2025-07-26 | Completed |  | 2025-08-26 | 2025-09-10 | Completed |  | 2025-08-22 |  | Not Started
Golden sample | [8 empty] | 2025-11-10 |  |  |  | 2025-08-22 |  | Not Started |  | 2025-08-18 | 2025-09-28 | Completed |  | 2025-09-16 |  | Not Started |  | 2025-11-05
BTRC doc | [8 empty] | 2025-11-10 |  |  |  | 2025-08-17 | 2025-08-02 | Completed |  | 2025-07-25 | 2025-07-20 | Completed | QC certificate done | 2025-09-01 |  | Not Started |  | 2025-09-21 |  | Not Started
SAR | [8 empty] | 2025-11-10 |  |  |  | 2025-07-29 | 2025-08-17 | Completed |  | 2025-08-08 | 2025-08-27 | Completed |  | 2025-09-01 |  | Not Started |  | 2025-09-21 |  | Not Started
Battery report(current & capacity) | [8 empty] | 2025-10-15 |  |  |  | 2025-08-17 | 2025-08-10 | Completed |  | 2025-08-18 | 2025-08-27 | Completed |  | 2025-09-01 |  | Not Started |  | 2025-08-22 |  | Not Started
IMEI TAC purchase | 2025-09-07 | 2025-09-07 | Completed | 35901568 |  |  |  | PROTONKING20250908 |  |  |  |  | 2025-07-19 | 2025-08-10 | Completed | 35560026 | 2025-07-26 | 2025-08-08 | Completed | 35176552 | 2025-08-22 |  | Started | Waiting for bank payment slip of GSM invoice | 2025-08-08 |  | Started
BTRC NOC | [12 empty] | 2025-08-25 |  | Started |  | 2025-08-30 | 2025-09-26 | Completed | 14.32.0000.000.501.47.0005.20.1346 | 2025-08-23 |  | Not Started |  |  |  | Not Started
STS Integration | [12 empty] | 2025-08-11 | 2025-08-28 | Completed |  | 2025-08-15 | 2025-09-10 | Completed |  | 2025-09-01 |  | Not Started |  |  |  | Not Started
SW Confirmation | [8 empty] | 2025-11-20 |  |  |  | 2025-09-05 | 2025-08-29 | Completed |  | 2025-09-10 | 2025-09-24 | Completed |  | 2025-09-15 |  | Not Started |  | 2025-10-25 |  | Not Started
User experience test | [12 empty] | 2025-08-19 |  | Completed |  | 2025-08-30 | 2025-09-10 | Completed |  | 2025-09-10 |  | Not Started |  |  |  | Not Started
HW Confirmation | [12 empty] | 2025-08-25 | 2025-08-17 | Completed |  | 2025-08-30 | 2025-09-18 | Completed |  | 2025-09-11 |  | Not Started |  |  |  | Not Started
TP film confirm |  |  |  |  | 2025-09-29 | 2025-09-03 | Completed | [5 empty] | 2025-07-29 | 2025-06-26 | Completed |  | 2025-07-26 | 2025-08-02 | Completed |  | 2025-08-20 | 2025-08-02 | Completed |  | 2025-10-13 | 2025-08-03 | Completed
Wrap film confirmation | [12 empty] | 2025-07-29 | 2025-06-26 | Completed |  |  |  | Pass |  |  |  | Pass |  |  |  | Pass
Label confirm |  |  |  |  | 2025-09-25 | 2025-09-10 | Started |  | 2025-10-15 |  |  |  | 2025-06-26 | 2025-06-26 | Completed |  | 2025-07-26 | 2025-07-29 | Completed |  | 2025-08-24 |  | Started | Battery Label confirmed. IMEI label not confirmed | 2025-10-13 | 2025-08-04 | Started | Battery Label confirmed. IMEI label not confirmed
Packaging list confirmation | [12 empty] | 2025-09-12 |  | Not Started |  | 2025-08-24 |  | Not Started |  | 2025-09-25 |  | Not Started |  | 2025-09-10 |  | Not Started
Jig list Confirmation | [8 empty] | 2025-10-25 |  |  |  | 2025-08-12 | 2025-08-12 | Completed | We asked SCM to pay for the Jig |  |  | Pass |  | 2025-09-16 |  | Not Started |  | 2025-09-10 |  | Pass
GB confirmation | [12 empty] | 2025-08-17 |  | Not Started |  | 2025-09-09 |  | Started | Designer is preparing the design | 2025-09-16 |  | Started | Designer is preparing the design | 2025-10-14 |  | Started | Designer is preparing the design
Reliability test confirmation | [12 empty] | 2025-08-21 |  | Started |  | 2025-08-15 |  | Not Started |  | 2025-10-11 |  | Not Started |  |  |  | Not Started
SOP confirmation | [8 empty] | 2025-10-25 |  |  |  | 2025-08-24 |  | Started |  | 2025-09-01 |  | Not Started |  | 2025-10-01 |  | Not Started |  |  |  | Not Started
SMT SW flash | [8 empty] | 2025-11-20 |  |  |  | 2025-09-12 |  | Not Started |  | 2025-09-12 |  | Not Started |  | 2025-09-20 |  | Not Started |  | 2025-10-14 |  | Not Started
SMT PCBA | [8 empty] | 2025-11-25 |  |  |  | 2025-09-13 |  | Not Started |  | 2025-09-13 |  | Not Started |  | 2025-10-11 |  | Not Started |  | 2025-11-11 |  | Not Started
Material readiness | [8 empty] | 2025-11-25 |  |  |  | 2025-09-14 |  | Not Started |  | 2025-09-14 |  | Not Started |  | 2025-10-12 |  | Not Started |  | 2025-11-12 |  | Not Started
QC and Inspection confirmation(China) | [8 empty] | 2025-11-27 |  |  |  | 2025-09-16 |  | Not Started |  | 2025-09-15 |  | Not Started |  | 2025-10-20 |  | Not Started |  | 2025-11-20 |  | Not Started
Shipment | [8 empty] | 2025-12-01 |  |  |  | 2025-09-25 |  | Not Started |  | 2025-09-18 |  | Not Started |  | 2025-10-21 |  | Not Started |  | 2025-11-21 |  | Not Started
RAW material Factory IN | [12 empty] | 2025-10-20 |  | Not Started |  | 2025-10-18 |  | Not Started |  | 2025-10-21 |  | Not Started |  |  |  | Not Started
IQC | [12 empty] | 2025-10-21 |  | Not Started |  | 2025-10-20 |  | Not Started |  | 2025-10-23 |  | Not Started |  |  |  | Not Started
Trial Production | [12 empty] | 2025-10-20 |  | Not Started |  | 2025-10-22 |  | Not Started |  | 2025-10-25 |  | Not Started |  |  |  | Not Started
MP | [12 empty] | 2024-10-26 |  | Not Started |  | 2025-10-25 |  | Not Started |  | 2025-10-27 |  | Not Started |  |  |  | Not Started
Launch | [12 empty] | 2024-11-01 |  | Not Started |  | 2025-10-27 |  | Not Started |  | 2025-10-28 |  | Not Started |  |  |  | Not Started
Formulas:
Neo = [Neo, row below]-8
Blast 3D = [Blast 3D, row below]-8

## Spare parts
Model Name | Supplier | Required Items | Requirement type | Qty(Pcs) | Reason | Unit Price | Total Value | Notes | Exchange Quantity | Number of HS can be produced(if applicable) | Number of GB in store (if applicable) | Number of GB required (if applicable) | PI date(in case of purchase) | PR(in case of purchase) | Added in Import plan? | Import plan month | Payment Date(in case of purchase) | Material readiness date | Notes on shipment | Shipment Date(opt.) | Shipment status | Remarks
E20 | CQ | LCD | Purchase | 400 | Order/ Lot closing | 500 |  | Spare parts are ready to ship | 0 | 400 | 1229 |  | 2025-05-13 | 55510048994 |  |  |  | 2025-07-22 | Already asked our SCM to take the shipment on 22nd July |  | Delivered
C15 | T-Source | LCD | Purchase | 400 | Order/ Lot closing | 392 |  | SCM asked for Packing list from the supplier. SCM is ready to ship these items | 0 | 400 | 599 |  | 2025-05-29 | 55510048994 |  |  |  | 2025-08-11 | SCM asked for Packing list from the supplier | Delivered on 9th September, 2025 | Delivered
D1 | T-Source | LCD | Purchase | 550 | Order/ Lot closing | 654.5 |  |  | 0 | 550 | 1031 |  | 2025-05-29 | 55510048994 |  |  |  | 2025-08-11 | SCM is ready to ship these items | Delivered on 9th September, 2025 | Delivered
C4b | CJMotors(Denny) | Camera | Purchase | 500 | Order/ Lot closing | 175 |  | Spare parts are sent to forwarder on 5th August | 0 | 500 | 1095 |  | 2025-07-15 | 55510050059 |  |  |  | 2025-08-02 | sent to forwarder(mr. Md.Jahir) on Aug.5. by SF(No.1553188377496). |  | Waiting for vessel
C16 | T-Source | Battery | FOC | 500 | Order/ Lot closing | 0 |  |  |  |  | 548
C16 | T-Source | Display/LCD | FOC | 350 | Order/ Lot closing | 0
C16 | T-Source | PCBA | FOC | 500 | Order/ Lot closing | 0
Infinity 8 | Hotwav | Mobile back part cover glue | Purchase | 200 | After Sales Service | 18.34 |  | Oogue carried 50pcs by hand. We handover 50 pcs to Mr. Kamrul Service on 3rd August Remaining 150pcs will be shipped in another way. |  |  |  |  | 2025-07-23 | 55510050999 |  |  | 2025-09-27 |  | 50 pcs of this items will be carried by Mr. Oogue |  | 50 pcs of back cover adhesive were handed over to Mr. Kamrul(Service) on 3rd August at PIP on his hand | Payment date 27th September. Asked SCM to take shipment. Oogue carried 50pcs by hand. We handover 50 pcs to Mr. Kamrul Service on 3rd August
Infinity 8 | Hotwav | Front Cover | Purchase | 50 | After Sales Service | 70 | [6 empty] | 2025-07-23 | 55510050999 |  |  |  |  | on 18th August I checked with Supplier… nobody contacted them regarding the payment |  |  | Asked and emailed for taking shipment on 18th August
Infinity 8 | Hotwav | LCD | Purchase | 50 | After Sales Service | 400 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | PCBA | Purchase | 30 | After Sales Service | 930 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Sub-Pcb | Purchase | 30 | After Sales Service | 63 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Back Cover | Purchase | 20 | After Sales Service | 24 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Battery | Purchase | 20 | After Sales Service | 84 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Fingerprint | Purchase | 20 | After Sales Service | 20 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Fpc Power | Purchase | 20 | After Sales Service | 3.4 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Front Camera | Purchase | 20 | After Sales Service | 22.4 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Receiver | Purchase | 20 | After Sales Service | 2.8 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Speaker | Purchase | 20 | After Sales Service | 9.8 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Antenna | Purchase | 10 | After Sales Service | 2.1 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Camera Lens | Purchase | 10 | After Sales Service | 10.5 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Middle Cover | Purchase | 10 | After Sales Service | 11 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Protective Film | Purchase | 10 | After Sales Service | 0.5 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Rear Camera | Purchase | 10 | After Sales Service | 17 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Sim Tray | Purchase | 10 | After Sales Service | 0.13 | [6 empty] | 2025-07-23 | 55510050999
Infinity 8 | Hotwav | Vibrator | Purchase | 10 | After Sales Service | 2.1 | [6 empty] | 2025-07-23 | 55510050999
Proton X20 Pro | Mobiwire | PCBA | Purchase | 50 | After Sales Service | 35.1 |  | All items have been arranged by the supplier to do the shipment |  |  |  |  | 2025-07-31 | 55510051587 |  |  | 2025-08-20 | ready to ship | Kevin(Mobiwire) is working on the shipment
Proton X20 Pro | Mobiwire | SUB PCBA | Purchase | 50 | After Sales Service | 1.5 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | FRONT HOUSING | Purchase | 50 | After Sales Service | 1.98 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | INCELL LCD | Purchase | 50 | After Sales Service | 9.2 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back Housing A | Purchase | 50 | After Sales Service | 0.42 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back Housing B | Purchase | 50 | After Sales Service | 0.24 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Middle Housing | Purchase | 50 | After Sales Service | 1.26 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Battery cover | Purchase | 50 | After Sales Service | 1.75 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back cover adhesive | Purchase | 200 | After Sales Service | 0.1 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Battery | Purchase | 50 | After Sales Service | 3.6 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Front Camera | Purchase | 50 | After Sales Service | 3.86 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back Camera | Purchase | 50 | After Sales Service | 3.86 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back Camera | Purchase | 50 | After Sales Service | 0.15 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Speaker | Purchase | 50 | After Sales Service | 0.3 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Receiver | Purchase | 50 | After Sales Service | 0.15 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Motor | Purchase | 50 | After Sales Service | 0.2 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Finger Print | Purchase | 50 | After Sales Service | 0.7 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | SIM Tray | Purchase | 50 | After Sales Service | 0.21 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Rubber | Purchase | 50 | After Sales Service | 0.02 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back Camera window | Purchase | 50 | After Sales Service | 0.08 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back sub Camera window | Purchase | 50 | After Sales Service | 0.08 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Flashlight | Purchase | 50 | After Sales Service | 0.03 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Screw | Purchase | 50 | After Sales Service | 0.02 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Main CAMERA WINDOW | Purchase | 50 | After Sales Service | 0.02 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | sub camera window | Purchase | 50 | After Sales Service | 0.03 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Rf cabel | Purchase | 50 | After Sales Service | 0.04 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Speaker Heat Film | Purchase | 50 | After Sales Service | 0.01 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | USB seal RUBBER | Purchase | 50 | After Sales Service | 0.025023 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Headset_RUBBER | Purchase | 50 | After Sales Service | 0.025023 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | FNT_CAM HEAT FILM | Purchase | 50 | After Sales Service | 0.053757 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Waterproof label | Purchase | 50 | After Sales Service | 0.01 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Screw label | Purchase | 50 | After Sales Service | 0.01 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | 3 layer film | Purchase | 50 | After Sales Service | 0.08 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Niddle | Purchase | 50 | After Sales Service | 0.07 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | TPU | Purchase | 50 | After Sales Service | 0.2 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Proton X20 Pro | Mobiwire | Back housing B heat film | Purchase | 50 | After Sales Service | 0.03 | [6 empty] | 2025-07-31 | 55510051587 |  |  |  | ready to ship
Glory i30 | Coosea | Battery | Purchase | 20 | After Sales Service | 5.4 |  | Total value $3016.05 |  |  |  |  | 2025-08-12 | 55510051586
Glory i30 | Coosea | TPU Cover | Purchase | 190 | After Sales Service | 0.25 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | PCBA | Purchase | 40 | After Sales Service | 28.815 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Sub PCBA | Purchase | 50 | After Sales Service | 0.87 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Front Housing assembly | Purchase | 150 | After Sales Service | 1.72 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | LCM assembly | Purchase | 150 | After Sales Service | 7.34 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Mid-frame assembly-Black | Purchase | 10 | After Sales Service | 2.16 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Mid-frame assembly-Gray | Purchase | 10 | After Sales Service | 2.16 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Battery cover assembly-Black | Purchase | 10 | After Sales Service | 1.51 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Battery cover assembly-Gray | Purchase | 10 | After Sales Service | 1.51 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Battery cover adhesive | Purchase | 300 | After Sales Service | 0.145 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Camera decoration assembly-Black | Purchase | 10 | After Sales Service | 0.438 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Camera decoration assembly-Gray | Purchase | 10 | After Sales Service | 0.438 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Card tray-Black | Purchase | 5 | After Sales Service | 0.231 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Card tray-Gray | Purchase | 5 | After Sales Service | 0.231 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Main rear camera lens | Purchase | 20 | After Sales Service | 0.096 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Sub-rear camera lens 1 | Purchase | 20 | After Sales Service | 0.023 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Sub-rear camera lens 2 | Purchase | 20 | After Sales Service | 0.015 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Flash light lens | Purchase | 20 | After Sales Service | 0.015 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Distance-sensing silicone sleeve | Purchase | 20 | After Sales Service | 0.013 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Front camera rubber sleev | Purchase | 20 | After Sales Service | 0.015 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Front camera | Purchase | 30 | After Sales Service | 1.047 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Main rear camera | Purchase | 30 | After Sales Service | 2.094 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | 2M Sub rear-camera | Purchase | 30 | After Sales Service | 0.558 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | 0.08M Sub rear-camera | Purchase | 30 | After Sales Service | 0.253 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Fingerprint module-Black | Purchase | 15 | After Sales Service | 0.768 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Fingerprint module-Gray | Purchase | 15 | After Sales Service | 0.768 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Receiver | Purchase | 30 | After Sales Service | 0.187 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Speaker | Purchase | 30 | After Sales Service | 0.28 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Motor | Purchase | 20 | After Sales Service | 0.158 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Coaxial cable | Purchase | 20 | After Sales Service | 0.05 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Side key fpc | Purchase | 20 | After Sales Service | 0.268 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | BB thermal conductive silicone | Purchase | 20 | After Sales Service | 0.013 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | PA thermal conductive silicone | Purchase | 20 | After Sales Service | 0.001 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Screw(M1.4*2.5MM) | Purchase | 20 | After Sales Service | 0.001 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Screw(M1.4*3.5MM) | Purchase | 20 | After Sales Service | 0.001 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Light guide pipe for ambient light sensor | Purchase | 10 | After Sales Service | 0.019 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | Wrap film | Purchase | 20 | After Sales Service | 0.125 | [6 empty] | 2025-08-12 | 55510051586
Glory i30 | Coosea | TP Film | Purchase | 50 | After Sales Service | 0.116 | [6 empty] | 2025-08-12 | 55510051586
X10 Pro | I-Swim | Front cover | Purchase | 200 | After Sales Service | 1.85 | [6 empty] | 2025-08-29 | 55510052922
X10 Pro | I-Swim | LCD | Purchase | 200 | After Sales Service | 9.8 | [6 empty] | 2025-08-29 | 55510052922
X10 Pro | I-Swim | LCD conductive fabric | Purchase | 200 | After Sales Service | 0.01 | [6 empty] | 2025-08-29 | 55510052922
ECO(5C) battery (CBU) Supplier Model Name :E1807 | Kingcomm | BL 5C Battery Size - 53.18 * 34 * 5.72mm | Purchase | 5000 | Order/ Lot closing | 0.35 | 1750 | [5 empty] | 2025-09-22 | 55510054946
C17(19C) battery (CBU) | Kingcomm | 19C Battery Size - 5.2*44*77.15mm Cell Size - 484473AR C14 - 1700, D1-1700 | Purchase | 1300 | Order/ Lot closing | 0.8 | 1040 | [5 empty] | 2025-09-22 | 55510054946
HULK(25BI) battery (CBU) Supplier Model Name :R2402 | Kingcomm | 25BI Battery Size - 78446.50mm Cell Size - 634475AR | Purchase | 2000 | Order/ Lot closing | 0.79 | 1580 | [5 empty] | 2025-09-22 | 55510054946
C16(19C) battery (CBU) Supplier Model Name :M2402M | Kingcomm | 19C Battery Size - 66.07*44*5.35mm Cell Size - 484461AR | Purchase | 1000 | Order/ Lot closing | 0.68 | 680 | [5 empty] | 2025-09-22 | 55510054946
Star(19C) battery (CBU) Supplier Model Name :KK240 | Kingcomm | 19C Battery Size - 72.16 * 44* 5mm | Purchase | 1000 | Order/ Lot closing | 0.65 | 650 | [5 empty] | 2025-09-22 | 55510054946
BATTERY LABEL COMMON | Kingcomm | Label Types : SAZ1000, SAZ2000A, SAZ3000A, SAZ1400, SAZ2000B | FOC | 12500 | Order/ Lot closing | 0 | 0 | [5 empty] | 2025-09-22 | 55510054946

## Import plan
Model Name | Particulars | Description | Qty | Reason | Total Value
X10 Pro | Spare parts of X10 Pro for our After Sales Service | LCD-200pcs Front Shell - 200pcs C. cloth - 200pcs | 200 set of LCD, Front shell and Conductive Cloth | After Sales Service | 2331.4
Battery Mold | Battery Mold for SKD battery production | 25BI Battery Mold - 1 piece 5C Battery Mold - 1 piece 19C Battery Mold - 1 piece | 3 pcs | Production | 1440

## Mini PC
TaskMaster
Milestone | Planned | Actual | Status | Note
PI Confirmation | 2025-06-17 | 2025-06-17 | Completed
ID confirmation | 2025-07-08 | 2025-07-03 | Completed
LC Transmit | 2025-07-05 | 2025-07-05 | Completed
PR | 2025-06-25 | 2025-06-27 | Completed | 55510050050
Sample(for HW and SW testing) | 2025-06-28 | 2025-06-30 | Completed
BOM Material Confirmation | 2025-07-01 | 2025-07-03 | Completed
BIOS Data Confirmation | 2025-06-29 | 2025-06-25 | Completed
SW Confirmation | 2025-06-29 | 2025-07-03 | Started
User experience test | 2025-07-02 | 2025-07-02 | Completed
HW Confirmation | 2025-07-04 | 2025-07-04 | Completed
Label confirm | 2025-06-26 | 2025-07-02 | Completed
Packaging list confirmation | 2025-07-25 | 2025-07-29 | Completed
Jig list Confirmation |  |  | Pass
GB confirmation |  |  | Pass
SOP confirmation | 2025-07-20 | 2025-07-20 | Completed
SMT SW flash | 2025-07-22 | 2025-07-23 | Completed
SMT PCBA | 2025-07-24 | 2025-07-25 | Completed
Material readiness | 2025-07-24 | 2025-07-25 | Completed
QC and Inspection confirmation(China) | 2025-07-30 | 2025-07-27 | Completed
Shipment | 2025-08-08 |  | Started | Due to the original vessel being rerouted to Hong Kong to handle transshipment containers from the grounded vessel at Nansha, severe overbooking has occurred. Therefore, this shipment has been rescheduled to the next available sailing: MAERSK DAVAO 534W ETD: 25 AUG.
RAW material Factory IN | 2025-09-25 |  | Not Started
IQC | 2025-09-26 |  | Not Started
Trial Production | 2025-09-28 |  | Not Started
MP | 2025-09-29 |  | Not Started
Launch | 2025-09-30 |  | Not Started

## Other Purchase
Item name | Item description | Supplier | Qty(Pcs) | Unit Price | Unit Weight(KG) | Total Value | Total Weight(KG) | Dimension | PR | Notes | PI Date | Payment Date | Material readiness date | Shipment Date(opt.) | Shipment status | Remarks
Battery Mold | EVO(25BI) battery mold Supplier Model Name :E1807 | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 |  | 2025-08-28
Battery Mold | i-Pro(5C) battery mold Supplier Model Name :KG200 | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 |  | 2025-08-28
Battery Mold | Jet4G(19C) battery mold Supplier Model Name :KK240L | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 |  | 2025-08-28

## data_sheet
Project Name | Order/shipment | Supplier | Qty | PI date | Material desc. | Items to add/modify in LCPI for SKD Battery
EVO | 6th | Kingcomm | 20000 | 2025-06-28 | Charger : CKD without housing, Battery: SKD | 1. Lithium ion cell ( instead of "Lithium ion Battery"). 2. Upper Cap & Lower Cap. 3. Protection Circuit Board
Hulk | 3rd | Kingcomm | 10000 | 2025-06-29 | Charger : CKD without housing, Battery: SKD | 1. Lithium ion cell ( instead of "Lithium ion Battery"). 2. Upper Cap & Lower Cap. 3. Protection Circuit Board
i-Pro | 1st | Kingcomm | 20000 | 2025-06-29 | Charger : CKD without housing, Battery: SKD | 1. Lithium ion cell ( instead of "Lithium ion Battery"). 2. Upper Cap & Lower Cap. 3. Protection Circuit Board
Neo | 1st | IMG | 15000 | 2025-06-27 | Charger : CKD without housing, Battery: SKD | 1. Lithium ion cell ( instead of "Lithium ion Battery"). 2. Upper Cap & Lower Cap. 3. Protection Circuit Board
[8 empty] | FOC | Material Fault
[8 empty] | Purchase | Incoming Short(material)
[8 empty] | Exchange | Production Fault
[7 empty] | Started |  | Order/ Lot closing
[7 empty] | Completed |  | After Sales Service
[7 empty] | Not Started |  | Production
Pending
Pass
Fail

## Spare_parts_rough
| Particulars | Description | Amount to be paid | Supplier | Shipment instruction
| Spare parts of Glory i30 for our After Sales Service | Our service team will use spare parts to solve after sales issues | 3016.05 | Coosea | The Spare Parts and Jig items will ship along with the raw material shipment of Glory i30
| Assembly Jigs of Glory i30 | Total 17 items needed to assemble Glory i30 | $ 1,577.70 | Coosea
| HS sample fee of Glory i30 | Coosea has committed 10pcs of samples. 5pcs will be provided free, 5pcs should be purchased | $ 243.50 | Coosea
|  | Total | 3259.55
| Item Code | Project Name | Order/shipment | Qty | Supplier Contact Person | Supplier Contact Email | Supplier Contact WeChat
| 751310 | HyperX | 1st | 3000 | Berry | berry.zheng@cooseagroup.com | wxid_h0sfy6dvxept21
Model name | Particulars | Description | Amount to be paid | Supplier | PR | Supplier Contact | Supplier email | Supplier WeChat
X10 Pro | Spare parts of X10 Pro for our After Sales Service dept | Our service team will use spare parts to solve after sales issues | $ 2331.40 | I-SWIM | 55510052922 | Sylvia | sylvialu@tirisen.com | sylvia20210908
|  | Total | 2331.4
|  |  |  | Item Code | Project Name | Order/shipment | Qty | PI date | Material Type
[5 empty] | King | 1st | 15000 | 2025-08-23 | Project: SKD, Charger: No, Battery : CBU
[5 empty] | Jet4g | 1st | 5000 | 2025-08-21 | Project: SKD, Charger : CKD without housing Type C cable, Battery: SKD
|  |  | Code | Item Name | Demand Qty(pcs)
|  |  | 656479799 | PROTON MOBILE X10 SMART FRONT COVER | 200
|  |  | 656479788 | PROTON MOBILE X10 SMART LCD | 200
| Model Name | Supplier | Required Items | Requirement type | Qty(Pcs) | Reason
| X10 Pro | I-Swim | Front cover | Purchase | 200 | After Sales Service
| X10 Pro | I-Swim | LCD | Purchase | 200 | After Sales Service
| X10 Pro | I-Swim | LCD conductive fabric | Purchase | 200 | After Sales Service
Item name | Item description | Supplier | Qty(Pcs) | Unit Price | Unit Weight(KG) | Total Value | Total Weight(KG) | Dimension | PR | PI Date | Supplier Contact Name | Supplier Contact Email | Supplier Contact WeChat
Battery Mold | EVO(25BI) battery mold Supplier Model Name :E1807 | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 | 2025-08-28 | Mason | sales03@kingcommtech.com | maosheng-wei
Battery Mold | i-Pro(5C) battery mold Supplier Model Name :KG200 | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 | 2025-08-28 | Mason | sales03@kingcommtech.com | maosheng-wei
Battery Mold | Jet4G(19C) battery mold Supplier Model Name :KK240L | Kingcomm | 1 | 480 | 21 | 480 | 21 | 23*11*14.6cm | 55510053050 | 2025-08-28 | Mason | sales03@kingcommtech.com | maosheng-wei
[5 empty] | Total Value | 1440

## Sheet1
Model | Activation(actual) | Activation(modified) | Imported Qty(modified)
ECO | 76901 | 92281.2 | 125000 | 0.2
EVO | 55908 | 67089.6
B1 | 47679 | 57214.8
HULK | 33315 | 39978
C4ix | 31102 | 37322.4
Particulars | Item | Qty | Unit cost | Total cost
Shipment cost | Tab | 1 | 5200 | 5200
Shipment cost | Smartphone(Glory i30) | 5 | 4500 | 22500
Shipment cost | Smaple IMEI label, Battery label, TPU case and Wrap film | 1 | 3500 | 3500
Shipment Cost | Needle for Smartphone(Infinity 8) glue dispensing | 1 | 3500 | 3500
Shipment Cost | Needle for Smartphone(X10 ) glue dispensing | 1 | 3500 | 3500
Shipment Cost | Headphone for PC | 3 | 3500 | 3500
Shipment cost | Metal mold for 67W charger | 1 | 3500 | 3500
|  |  | Total | 45200
Project Name | Order/shipment | Short spec | Supplier | Qty | PI date | PR | IMEI TAC | BTRC Imp. NOC | Material desc.
King | 1st | Display:1.77'' Chipest:6531E Camera with flash, No Torch, Memory:32M+32M Speaker:2030， Type C | T-World | 15000 | 2025-08-23 | Applied |  | Need to apply | Project: SKD, Charger: No, Battery : CBU
Jet4g | 1st | 2.4 inch QVGA ( T127) Battery : 2000 mAh Wireless FM Camera - Front: 0.08MP, Rear: 0.08MP+flash | Kingcomm | 5000 | 2025-08-22 | Applied |  | Need to apply | Project: SKD, Charger : CKD without housing Type C cable, Battery: SKD

## ETC & Machine
PR number | Code | Item Name | QTY | Remarks
55510050840 | 1228976198 | GLUE SPRAY MACHINE | 1 | Five axis glue spraying machine
55510050840 | 1250322056 | PLASMA SURFACE TREATMENT MACHINE | 1 | Desktop plasma cleaning machine
55510050840 | 533150210 | SEALER MACHINE FOR POLY SEALING | 1 | Plastic bag sealing and Cutting Machine
55510050840 | 330601025 | ESD SHOES FOR CLEAN ROOM | 75 | ESD Slipper
55510050840 | 527084402 | TAPE DISPENSER MACHINE 1INCH | 2 | Automatic Tape Dispenser
55510050840 | 526392100 | COSTAPE CUTTER M/C | 2 | Tape Cutter Machine
55510050840 | 1250396652 | AUTO LABEL/BARCODE PASTING MACHINE | 1 | Semi-automatic corner labeling machine
55510050840 | 527605845 | MOBILE CHARGING STATION | 1 | Semi-automatic Charger insertion machine
55510050840 | 626856000 | AMPLIFIER | 2 | GPS transponder
55510050840 | 627299214 | SERIAL TO USB CONVERTER | 15 | GPIB-USB Cable
55510050840 | 526904319 | ENCODER CABLE | 10 | GPIB Cable
55510050840 | 500014713 | DIGITAL ELECTRIC CONTACT PRESSURE GAUGE | 1 | Digital Pressure Gauge

## Sheet2
Project Name | Order/shipment | Qty | FOB | Material desc. | Month |  | Project Name |  | Order/shipment | Qty | Spec | Material desc. | Remark
Style | 1st | 30000 |  | Handset: CKD Charger : CKD without housing, Type C cable, Battery: SKD | September |  | ECO25 |  | 3rd | 15000 | 1.77'' QQVGA, MTK6261M, 1000 mAh, no camera, Wireless FM, F5 torch | Handset: CKD Charger : CKD without housing, Type B cable, Battery: SKD | At first the project was 20K SKD, then it was converted to 15K CKD. Battery converted to SKD from CBU
i-Pro | 2nd | 20000 |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD | September
ECO | 7th | 30000 |  | Handset: SKD Charger : CKD without housing, B type cable, Battery: CBU | September
ECO25 | 3rd | 15000 |  | Handset: CKD Charger : CKD without housing, B type cable, Battery: CBU | September
E30 | 3rd | 20000 |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: CBU | September
Glow | 1st | 20000 |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD | October
EVO | 8th | 40000 |  | Handset: SKD Charger : CKD without housing, Type B Cable. Battery: SKD | October
Hulk | 5th | 20000 |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: SKD | October
PowerX | 4th | 20000 |  | Handset: SKD Charger : CKD without housing, Type C cable, Battery: CBU | October
| Total | 215000
Project Name | Order/shipment | Short spec | Supplier | Qty | Material desc. | Remarks
Style CKD | 1st | 2.4'' QVGA, SC6533G -Battery : 2500 mAh - speaker, Receiver& Vibrator 3 in 1 , no camera -Wireless -FM , F7 Torch | Kingcomm | 30000 | Handset: CKD | New Model
Charger : CKD without housing, Type C cable,
Battery: SKD
i-Pro | 2nd | 2'', MTK6261M, Battery : 1000 mAh, F5 torch, no camera, Type C | Kingcomm | 20000 | Handset: SKD
Charger : CKD without housing, Type C cable,
Battery: SKD
ECO | 7th | 1.77'' MTK6261M, 1000 mAh , no camera | Kingcomm | 30000 | Handset: SKD | Battery changed to SKD from CBU
Charger : CKD without housing, B type cable,
Battery: SKD
ECO25 | 3rd | 1.77'' QQVGA, MTK6261M, 1000 mAh, no camera, Wireless FM, F5 torch | Kingcomm | 15000 | Handset: CKD | At first the project was 20K SKD, then it was converted to 15K CKD . Battery converted to SKD from CBU
Charger : CKD without housing, B type cable,
Battery: SKD
E30 | 3rd | 2.4'' QQVGA, MTK6261M, 2000 mAh, no camera, Wireless FM, F5 torch | Kingcomm | 20000 | Handset: SKD | Battery changed to SKD from CBU
Charger : CKD without housing, Type C cable,
Battery: SKD
Glow | 1st | 2.8'' QVGA, MTK6261M, Battery : 2500 mAh, | Kingcomm | 20000 | Handset: SKD | New Model
|  | speaker, Receiver& Vibrator 3 in 1 , VGA camera, Wireless FM, F8 Torch |  |  | Charger : CKD without housing, Type C cable,
Battery: SKD
EVO | 8th | 2'', MTK6261M, 3000 mAh, F7 torch, camera | Kingcomm | 40000 | Handset: SKD
Charger : CKD without housing, Type B Cable.
Battery: SKD
Hulk | 5th | 2.4'', MTK6261D, 3000 mAh, strip torch, camera | Kingcomm | 20000 | Handset: SKD
Charger : CKD without housing, Type C cable,
Battery: SKD
PowerX | 4th | 2.4'', MTK6261M, 3000 mAh, F7 torch, camera, Type C | Kingcomm | 20000 | Handset: SKD
Charger : CKD without housing, Type C cable,
Battery: CBU
Model Name | Supplier | Required Items | Requirement type | Qty(Pcs) | Reason | Unit Price | Total Value | PR | Supplier Contact | Supplier Email | Supplier WeChat
ECO(5C) battery (CBU) Supplier Model Name :E1807 | Kingcomm | BL 5C Battery Size - 53.18 * 34 * 5.72mm | Purchase | 5000 | Order/ Lot closing | 0.35 | 1750 | 55510054946 | Mason | sales03@kingcommtech.com | maosheng-wei
C17(19C) battery (CBU) | Kingcomm | 19C Battery Size - 5.2*44*77.15mm Cell Size - 484473AR C14 - 1700, D1-1700 | Purchase | 1300 | Order/ Lot closing | 0.8 | 1040 | 55510054946
HULK(25BI) battery (CBU) Supplier Model Name :R2402 | Kingcomm | 25BI Battery Size - 78446.50mm Cell Size - 634475AR | Purchase | 2000 | Order/ Lot closing | 0.79 | 1580 | 55510054946
C16(19C) battery (CBU) Supplier Model Name :M2402M | Kingcomm | 19C Battery Size - 66.07*44*5.35mm Cell Size - 484461AR | Purchase | 1000 | Order/ Lot closing | 0.68 | 680 | 55510054946
Star(19C) battery (CBU) Supplier Model Name :KK240 | Kingcomm | 19C Battery Size - 72.16 * 44* 5mm | Purchase | 1000 | Order/ Lot closing | 0.65 | 650 | 55510054946
BATTERY LABEL COMMON | Kingcomm | Label Types : SAZ1000, SAZ2000A, SAZ3000A, SAZ1400, SAZ2000B | Purchase | 12500 | Order/ Lot closing | 0 | 0 | 55510054946
[6 empty] | SUM | 5700

## Sheet3
Model | E6766 | N81 Ultra | H93E | S87 | P71 | X100 | H67J2
ID
Price | 4GB+128GB = $55.5 6GB+128GB = $58.5 | 6GB+128GB = $60.5 8GB+128GB = $62 | G81: $58.6 G88: $59.2 | 56.8 | 6GB+128GB:$60.60 6GB+256GB:$64.50 | 6GB+128GB =$66.7 8GB+256GB = $84 | 4GB+128GB : $69.9 6GB+128GB : $78.5
OS (Operating System) | Android 15 or above | Android 15 or above | Android 15 or above | Android 15 | Android 15 | Android 16 | Android 15 or above
Screen/Display/LCD | 6.67” HD+ Punch-hole 120Hz 480Nits | 6.95”FHD+ Punch -hole | 6.745”,HD+(720*1600),waterdrop, Max Refresh Rate:90Hz, Water-drop display | 6.79'', HD+, INCELL, Punch-hole display | 7.2'' HD+, Incell, IPS,PH | 6.9" waterdrop | 6.67"IPS, HD+, Punch-hole
Camera (Rear & Front) | Front: 8MP Rear: 50MP + CIF&CIF | Front:16MP FF Rear:48MP AF | Triple Camera : Main - 64 MP. Macro - 2MP shielding - 0.08MP Front Camera : 16MP | Rear Camera : 50MP Front Camera : 8MP | Rear:50MP Front: 8MP | Front: 16MP Rear: 64MP | Front: 8MP Rear: 50MP + .8MP Sony 852 sensor
Memory (RAM + ROM) | 4GB+128GB 6GB+128GB | 8GB+128GB 6GB+128GB UFS | 4GB+128GB 6GB+128GB 8GB+128GB | 4GB+128GB | 6GB+128GB/256GB | 6GB+128GB | 4GB+128GB 6GB+128GB
Battery | 6000mAh | 5000mAh | 5000mAh | 5000mAh | 5000mAh | 6180mAh | 6000mAh
CPU | MTK G81 | T606 (+$1.7 for T615) | Mediatek G81 Mediatek G88 | Mediatek G81 | Mediatek G81 | T7250/12nm | Mediatek G81
Fingerprint | Side mounted fingerprint | side | Yes | Side | Side | Side fingerprint | Side
Charging Capacity | 18W | 18W | 18W | 18W | 20W | PD 20W | 18W
Ingress Protection(IP) Water and Dust resistance | IP64 | NO | IP53 | IP53 | IP53 | IP53 | IP64